## Stakeholder Map
Name | Role | Stated Priority | Underlying Concern | Likely Position on Recommendation | Key Quote | Facilitation Risk | FACILITATOR: Watch out for
Henrik Strand | CEO | Fix cost structure without sacrificing DACH growth story | Publicly committed to Network 2030 at investor day. Personal credibility on the line. Needs a clear, defensible decision — not a framework. | Broadly supportive of bold action. Will back the recommendation if it is clear and the CFO is aligned. | 'I don't want a report telling me what I already know. I want to know what we should do and why we should be confident.' | LOW — if CFO and COO are aligned, Henrik will follow. If they disagree, he will delay. | FACILITATOR: His support is conditional on CFO alignment. If Ingrid raises the cash flow bridge in the room and it's not prepared, Henrik's confidence will visibly drop. Prepare it.
Ingrid Hoffmann | CFO | Return on Gdansk investment. Covenant compliance. Cash flow visibility. | Has been managing nervous board members for 18 months. Sees the covenant breach risk clearly. Needs numbers not narrative. Does not trust the COO's timeline. | Will challenge any recommendation that doesn't include a credible cash flow bridge and covenant compliance path. | 'Show me the cash flow bridge. Not the strategy slides — the cash flow bridge.' | HIGH — if the cash flow bridge is not ready, she will block the recommendation in the room. | FACILITATOR: CRITICAL AMBIGUITY — Ingrid wants to exit co-manufacturing (contract expires Dec 2024). Lars wants to keep it for fixed cost coverage. This disagreement has NOT been resolved before the steering committee. It will surface in the room. Decide which recommendation to make and pre-brief both.
Lars Eriksson | COO | Operational stability during transition. Protecting Nordic service levels. | Organisation is tired after 2 years of integration. Worried his team can't absorb another major change programme. Wants 36-month implementation not 18. | Broadly aligned on the direction but will push hard on pace. His read of the OTIF root cause (logistics) differs from Per Hansson's (planning). He doesn't know you know this. | 'The right answer implemented badly is worse than a slightly sub-optimal answer implemented well.' | MEDIUM — will push back on timeline. Manageable if he feels heard. | FACILITATOR: AMBIGUITY — Lars believes OTIF is primarily a logistics problem. Per Hansson (not in the room) has shown it's primarily a forecasting/planning problem. If the recommendation addresses logistics only, Lars will endorse it but the OTIF problem won't actually be fixed. Do you surface Per's analysis? Lars will be surprised and possibly defensive.
Sofia Lindqvist | Head of Commercial | Protect DACH growth momentum. Protect customer relationships built over 18 months. | Believes DACH margins are healthy (she hasn't seen full cost-to-serve including logistics). Will be surprised to learn several DACH accounts are margin-negative. | Potential surprise objection on service level disruption. Has not been closely involved in analysis. Will react rather than having shaped the recommendation. | 'I'm supportive of this work but I need to understand the service level implications before I can endorse a specific direction.' | HIGH — she is a wildcard. She hasn't seen the full DACH cost picture. She has customer relationships to protect. Brief her separately before the SteerCo. | FACILITATOR: CRITICAL AMBIGUITY — Sofia thinks DACH margins are good. The data shows several DACH accounts are margin-negative when logistics is fully loaded. When she sees this in the SteerCo, her reaction could go either way: (1) constructive — 'OK now I understand why we need to change', or (2) defensive — 'this is an ops problem not a commercial problem.' Her reaction depends on how the recommendation is framed. If it's framed as 'the commercial team has been growing us into losses,' she will push back hard. Frame it as 'the network has not kept up with the commercial ambition.'
Marek Kowalski | Site Director, Gdansk (not on SteerCo) | Clear mandate for Gdansk's role. Volume commitments. Certainty for his team. | Two years of uncertainty. Knows his site has better capabilities than HQ credits. Will interpret any ambiguity as a threat. | Not in the room but his buy-in is critical for implementation. A poorly communicated decision could cause further talent loss at Gdansk. | 'Give me volume commitments and a clear mandate. That's all I need.' | LOW in the room. HIGH for implementation. | FACILITATOR: Marek mentioned two potential contract manufacturing customers approaching Gdansk during the engagement. This has NOT been fed back to the SteerCo. If the recommendation includes surplus capacity at Gdansk, this is a relevant option worth raising. Decide whether to include it in the recommendation.

## Stakeholder Engagement Log
# | Date | Week | Stakeholder | Type | Topic | Sentiment | Key Statement / Action | Follow-up Required? | Followed Up? | FACILITATOR: Note
1 | Sep 02 | Wk 1 | Henrik Strand | Kick-off meeting | Project scope and ambition | Positive | 'I want a clear answer, not a range of options. Make a recommendation.' | Yes — confirm scope | Yes
2 | Sep 02 | Wk 1 | Ingrid Hoffmann | Kick-off meeting | Financial parameters and constraints | Concerned | 'The covenant situation is more urgent than people realise. Q3 2025 is not far away.' | Yes — get covenant details | Yes
3 | Sep 03 | Wk 1 | Lars Eriksson | Kick-off meeting | Operational scope and data access | Positive | 'Happy to give full access. Warn you some of the data is messy.' | Yes — data access | Yes
4 | Sep 10 | Wk 2 | Ingrid Hoffmann | Email | Request for preliminary cost data | Concerned | 'When can I expect to see the cost-to-serve analysis? I need it before the board call on Oct 4.' | Yes — send prelim analysis | Yes — sent Sep 18
5 | Sep 12 | Wk 2 | Marek Kowalski | On-site visit | Site tour and operational briefing | Initially defensive, then open | 'I hope this is different from the last consulting review. That one went nowhere.' | Yes — follow up on co-man query | Yes | FACILITATOR AMBIGUITY: Marek mentioned a previous consulting review that 'went nowhere.' This is the second reference to prior consulting work that didn't land. The SteerCo does not know the team is aware of this history. Could be relevant to how the recommendation is positioned.
6 | Sep 19 | Wk 3 | Sofia Lindqvist | Introductory call | Commercial context and DACH relationships | Positive | 'Happy to help. I assume the network changes won't affect the customer commitments we've made?' | Yes — clarify service level assumptions | Partial — not fully resolved | FACILITATOR AMBIGUITY: Sofia assumed service levels would be protected. This assumption has not been formally challenged. She is entering the SteerCo with an expectation that may not be met by the recommendation.
7 | Sep 24 | Wk 3 | Ingrid Hoffmann | Email | Follow-up on cash flow bridge | Concerned | 'I still haven't seen the cash flow bridge I asked for. This is my primary concern.' | Yes — urgent | Partial
8 | Oct 01 | Wk 4 | Lars Eriksson | Workshop | Current state diagnostic findings | Neutral | 'Some of this I knew. The DACH logistics numbers are worse than I realised.' | Yes — align on root cause of OTIF | Partial — not resolved
9 | Oct 01 | Wk 4 | Sofia Lindqvist | Workshop | Current state diagnostic findings | Concerned | 'Wait — are you saying some of our DACH accounts are loss-making? That's not my understanding.' | Yes — urgent briefing needed | NO — NOT DONE | FACILITATOR AMBIGUITY: CRITICAL. Sofia directly questioned whether DACH accounts are loss-making. This was flagged for follow-up but was NOT done. She is going into the SteerCo without a full briefing on the DACH cost picture. This is the highest stakeholder management risk in the engagement.
10 | Oct 08 | Wk 5 | Henrik Strand | Steering committee update | Mid-point progress review | Positive | 'Good progress. I want the recommendation to be bold. Don't give me a 'it depends' answer.' | No | N/A
11 | Oct 08 | Wk 5 | Ingrid Hoffmann | Steering committee update | Mid-point progress review | Concerned | 'I'm still waiting for the cash flow bridge. I've asked three times now.' | Yes — critical | Partial — draft sent
12 | Oct 10 | Wk 5 | Marek Kowalski | Phone call (unscheduled) | Gdansk team morale and uncertainty | Concerned | 'My best two production supervisors have had job offers. I need something to tell them. Soon.' | Yes — accelerate timeline communication | Yes — brief call back | FACILITATOR AMBIGUITY: Marek mentioned talent retention risk at Gdansk. This has NOT been included in the risk section of the recommendation deck. Should it be? It changes the urgency argument for giving Gdansk a clear mandate quickly.
13 | Oct 15 | Wk 6 | Lars Eriksson | One-to-one | Implementation timeline | Concerned | 'I can do 24 months if I have to. I cannot do 18. The organisation is not ready.' | Yes — timeline alignment | Partial
14 | Oct 22 | Wk 7 | Per Hansson | One-to-one | OTIF root cause analysis | Positive | 'The data backs my view — it's a forecasting problem, not logistics. I can share the analysis.' | Yes — incorporate in findings | Yes — reviewed | FACILITATOR AMBIGUITY: Per's analysis directly contradicts Lars's stated view on OTIF root cause. The team has this data. Does the recommendation address the planning failure or only the logistics/network question? If planning is not addressed, OTIF will not improve even after the network is redesigned.
15 | Oct 28 | Wk 8 | Ingrid Hoffmann | Email | Pre-read feedback | Concerned | 'The pre-read is useful but the cash flow bridge is still not clear enough. I need to see monthly cash flow for 36 months, not annual.' | Yes — revise cash flow bridge | In progress
16 | Oct 29 | Wk 8 | Lars Eriksson | Email | Pre-read feedback | Neutral | 'I can live with the recommendation direction. My concern is the 18-month phasing. I want this discussed at the SteerCo.' | No — to be raised in SteerCo | N/A
17 | Oct 30 | Wk 8 | Sofia Lindqvist | Email | Pre-read feedback | Concerned | 'I haven't had a chance to fully digest the DACH account economics section. I may have questions in the SteerCo. Can someone brief me beforehand?' | YES — URGENT PRE-BRIEF NEEDED | NOT DONE | FACILITATOR AMBIGUITY: CRITICAL. Sofia has explicitly requested a pre-brief before the SteerCo. This has NOT been done. She is going in underprepared and has flagged the DACH economics section as the source of concern. Highest risk item going into the meeting.
18 | Oct 31 | Wk 8 | Henrik Strand | Email | Pre-read acknowledgement | Positive | 'Looks good. Make sure the recommendation is crisp. One page if possible.' | No | N/A
19 | Nov 01 | Wk 8 | Marek Kowalski | Site visit (final) | Site capability presentation | Positive | 'I have prepared a full capability briefing for the team. I want HQ to see what we can do here.' | Yes — incorporate site capability in recommendation | Partial | FACILITATOR AMBIGUITY: Marek prepared a capability presentation that nobody at HQ has formally received. He believes it has been shared. It hasn't been included in the SteerCo pre-read. If he finds out during the meeting that his presentation wasn't used, this will damage trust at a critical moment.
20 | Nov 04 | SteerCo-1 | All | Steering committee — RECOMMENDATION | Final recommendation presentation | TBD | TBD | TBD | TBD | TODAY

## Pre-read Feedback
Stakeholder | Role | Feedback | Key concern raised | FACILITATOR: Implication
Henrik Strand | CEO | The pre-read is well structured. The diagnosis is clear and I agree with the framing. My main request: make the recommendation crisper. I want to be able to read the recommended option in two sentences. I also want to understand the downside scenario — what happens if we do nothing. | Wants crisper recommendation + downside scenario | Manageable. Prepare a 'do nothing' scenario with explicit covenant breach timing.
Ingrid Hoffmann | CFO | The strategic logic is sound. My outstanding concern is the cash flow bridge — the annual view in the pre-read is not sufficient for board purposes. I need monthly cash flow for 36 months showing the capex phasing, working capital impact, and covenant headroom at each point. I am also unclear on the co-manufacturing exit treatment — is the Dec 2024 contract expiry factored in? I want this addressed before or during the SteerCo. | Cash flow bridge not detailed enough. Co-manufacturing exit not clear. | CRITICAL: Cash flow bridge must be ready for SteerCo. Co-manufacturing exit recommendation must be explicit — she will not let this pass without an answer.
Lars Eriksson | COO | I can broadly support the direction. The part I want to discuss further is the implementation timeline. 18 months assumes a level of organisational capacity that I am not confident we have right now. The Gdansk team in particular has been through a lot. I would want to see a detailed mobilisation plan before committing to 18 months. I also want to flag that the OTIF root cause analysis in the pre-read attributes the problem primarily to logistics. My view is that this is correct but I know the planning team has a different view — I want that to be discussed openly rather than assumed away. | Timeline concern: 18 months too aggressive. Wants OTIF root cause discussed openly. | MEDIUM RISK: Lars is flagging the Per Hansson tension openly. He knows there is a disagreement. This will come up in the SteerCo. Prepare to present both views and the data that supports Per's analysis — but do so diplomatically, as Lars is the one who will own implementation.
Sofia Lindqvist | Head of Commercial | I have read the pre-read and I have questions about the DACH section that I wasn't able to resolve before writing this feedback. Specifically: the cost-to-serve analysis shows several DACH accounts with margins below 10% when logistics is fully loaded. This is not how I have understood the DACH economics. If this is correct it has significant implications for our commercial strategy that I don't think have been fully worked through. I requested a briefing before the SteerCo but wasn't able to get one. I will raise these questions in the meeting. | Surprised by DACH account margins. Was not pre-briefed. Will raise questions in SteerCo. | CRITICAL: Sofia is going in underprepared and surprised. She has explicitly signalled she will ask questions in the room. Two options: (1) call her before the SteerCo and walk her through the DACH economics — strongly recommended. (2) let it surface in the room and manage it live — high risk, could derail the meeting. The framing matters: 'the network hasn't kept up with commercial ambition' not 'the commercial team has been selling at a loss.'
Marek Kowalski | Site Director, Gdansk (sent informally) | I have received the pre-read via Lars. I am supportive of the direction and I am grateful that the Gdansk capabilities are represented fairly. I prepared a site capability summary that I shared with the project team last week — I hope this has been incorporated. My only request: when the SteerCo discusses the Gdansk mandate, please make sure the message is clear and specific. Vague support for Gdansk is not useful to me — I need volume commitments. | Expects his capability presentation was incorporated (it wasn't). Wants specific volume commitments. | FACILITATOR: Marek believes his capability summary was incorporated — it was not included in the pre-read. He may reference it in the SteerCo. Decide whether to reference it proactively. His ask for specific volume commitments is legitimate and should be addressed in the recommendation.